## Executive_Dashboard
Mars Rover Delivery Management Dashboard & RAID Tracker
Average Velocity | 92.695
Total Story Points Delivered | 1269
Milestones Complete | 10
Open Risks | 0
Project Health | GREEN

## Team_Members
Emp ID | Name | Role | Allocation %
TM01 | Aarav Sharma | Project Lead | 100
TM02 | Priya Patel | Systems Engineer | 100
TM03 | Rohan Gupta | Mechanical Engineer | 100
TM04 | Ananya Singh | Mechanical Engineer | 100
TM05 | Vivek Rao | Embedded Engineer | 100
TM06 | Neha Verma | Software Engineer | 100
TM07 | Karan Joshi | Software Engineer | 100
TM08 | Aditya Mehta | Electronics Engineer | 100
TM09 | Ishita Roy | Science Lead | 100
TM10 | Rahul Nair | Testing Engineer | 100
TM11 | Sneha Kulkarni | Documentation & PMO | 100

## Sprint_Metrics
Sprint | Planned SP | Completed SP | Velocity %
S1 | 40 | 35 | 87.5
S2 | 45 | 42 | 93.3
S3 | 50 | 46 | 92
S4 | 52 | 48 | 92.3
S5 | 55 | 51 | 92.7
S6 | 58 | 54 | 93.1
S7 | 60 | 56 | 93.3
S8 | 62 | 58 | 93.5
S9 | 65 | 59 | 90.8
S10 | 68 | 63 | 92.6
S11 | 70 | 65 | 92.8
S12 | 72 | 67 | 93.1
S13 | 75 | 69 | 92
S14 | 78 | 71 | 91
S15 | 80 | 75 | 93.8
S16 | 82 | 76 | 92.7
S17 | 85 | 80 | 94.1
S18 | 87 | 82 | 94.3
S19 | 90 | 84 | 93.3
S20 | 92 | 88 | 95.7

## Capacity
Sprint | Capacity Hours | Utilized Hours
S1 | 880 | 770
S2 | 860 | 802
S3 | 880 | 809
S4 | 880 | 812
S5 | 860 | 797
S6 | 880 | 819
S7 | 880 | 821
S8 | 860 | 804
S9 | 880 | 799
S10 | 880 | 814
S11 | 860 | 798
S12 | 880 | 819
S13 | 880 | 809
S14 | 860 | 782
S15 | 880 | 825
S16 | 880 | 815
S17 | 860 | 809
S18 | 880 | 829
S19 | 880 | 821
S20 | 860 | 823

## Milestones
ID | Milestone | Month | Status
M1 | Design Freeze | 1 | Complete
M2 | Prototype Build | 2 | Complete
M3 | Power Validation | 3 | Complete
M4 | Software Alpha | 4 | Complete
M5 | Sensor Integration | 5 | Complete
M6 | Autonomous Drive Test | 6 | Complete
M7 | Payload Integration | 7 | Complete
M8 | Environmental Qualification | 8 | Complete
M9 | System Integration | 9 | Complete
M10 | Competition Readiness | 10 | Complete

## RAID_Log
ID | Type | Description | Status
R01 | Risk | Sensor delivery delay | Closed
R02 | Risk | Battery overheating | Closed
A01 | Assumption | Components within budget | Valid
A02 | Assumption | Test facility available | Valid
I01 | Issue | Navigation instability | Resolved
I02 | Issue | Suspension failure | Resolved
D01 | Dependency | Sensor vendor | Closed
D02 | Dependency | Test ground access | Closed